## Daily Schedule
Week | Day | Date | Day of Week | Phase | Target | Hours | Completed | Notes | Specific Tasks
1 | 1 | 2026-05-19 | Tuesday | Phase 0: Setup & Initial Pitch | Environment Setup | 3 | FALSE |  | Install Git, create GitHub repo, install Vivado, Python with Qiskit
1 | 2 | 2026-05-20 | Wednesday | Phase 0: Setup & Initial Pitch | Repo Structure | 2 | FALSE |  | Create folder structure: /docs, /src/verilog, /src/python, /sim, /results
1 | 3 | 2026-05-21 | Thursday | Phase 0: Setup & Initial Pitch | Literature Deep Dive | 4 | FALSE |  | Re-read Q-xApp paper + 2026 tensor network paper. Take structured notes.
1 | 4 | 2026-05-22 | Friday | Phase 0: Setup & Initial Pitch | Understanding Grover | 3 | FALSE |  | Implement Grover's algorithm in Python/Qiskit for 4 items. Verify it works.
1 | 5 | 2026-05-23 | Saturday | Phase 0: Setup & Initial Pitch | Understanding Tensor Networks | 3 | FALSE |  | Implement simple Matrix Product State (MPS) in Python.
1 | 6 | 2026-05-24 | Sunday | Phase 0: Setup & Initial Pitch | Problem Formulation | 2 | FALSE |  | Write PRB allocation as search problem. Define tensors.
1 | 7 | 2026-05-25 | Monday | Phase 0: Setup & Initial Pitch | Pitch Preparation | 3 | FALSE |  | Create 10-slide pitch deck: Problem → Gap → Solution → Timeline
2 | 8 | 2026-05-26 | Tuesday | Phase 0: Setup & Initial Pitch | Pitch Rehearsal | 2 | FALSE |  | Practice pitch. Anticipate questions. Refine slides.
2 | 9 | 2026-05-27 | Wednesday | Phase 0: Setup & Initial Pitch | Initial Pitch Presentation | 2 | FALSE |  | Present to supervisor/peers. Get feedback.
2 | 10 | 2026-05-28 | Thursday | Phase 0: Setup & Initial Pitch | Incorporate Feedback | 3 | FALSE |  | Update project plan based on feedback. Finalize scope.
2 | 11 | 2026-05-29 | Friday | Phase 0: Setup & Initial Pitch | Tensor Network Design for Grover | 4 | FALSE |  | Design how Grover's diffusion operator becomes a tensor contraction.
2 | 12 | 2026-05-30 | Saturday | Phase 0: Setup & Initial Pitch | Python Prototype | 4 | FALSE |  | Implement Grover using tensor networks for N=4,8,16 items.
2 | 13 | 2026-05-31 | Sunday | Phase 0: Setup & Initial Pitch | Validate Prototype | 3 | FALSE |  | Compare tensor network Grover against Qiskit Grover.
2 | 14 | 2026-06-01 | Monday | Phase 0: Setup & Initial Pitch | Hardware Resource Estimation | 2 | FALSE |  | Estimate BRAM, DSP, LUT requirements.
3 | 15 | 2026-06-02 | Tuesday | Phase 1: FPGA Architecture Design | Study Quad-Tile | 3 | FALSE |  | Re-implement paper's quad-tile matrix multiplication in Python.
3 | 16 | 2026-06-03 | Wednesday | Phase 1: FPGA Architecture Design | Design Contraction Unit | 4 | FALSE |  | Draw architecture diagram for tensor contraction unit.
3 | 17 | 2026-06-04 | Thursday | Phase 1: FPGA Architecture Design | Design SVD Unit | 4 | FALSE |  | Design parallel SVD unit using quad-tile (Jacobi method).
3 | 18 | 2026-06-05 | Friday | Phase 1: FPGA Architecture Design | Design Grover Diffusion | 4 | FALSE |  | Map Grover's diffusion operator to tensor contraction.
3 | 19 | 2026-06-06 | Saturday | Phase 1: FPGA Architecture Design | Write Architecture Document | 4 | FALSE |  | Create /docs/architecture.md with block diagrams, data flow.
3 | 20 | 2026-06-07 | Sunday | Phase 1: FPGA Architecture Design | Review Architecture | 2 | FALSE |  | Get feedback on architecture from supervisor/peer.
3 | 21 | 2026-06-08 | Monday | Phase 1: FPGA Architecture Design | Buffer Day | 3 | FALSE |  | Catch up on incomplete tasks from Week 3.
4 | 22 | 2026-06-09 | Tuesday | Phase 1: FPGA Architecture Design | BRAM Controller Design | 4 | FALSE |  | Design BRAM storage, write address generation logic.
4 | 23 | 2026-06-10 | Wednesday | Phase 1: FPGA Architecture Design | DSP48E Configuration | 3 | FALSE |  | Design multiply-accumulate pipeline using DSP48E slices.
4 | 24 | 2026-06-11 | Thursday | Phase 1: FPGA Architecture Design | Control FSM Design | 4 | FALSE |  | Design FSM: IDLE → LOAD → CONTRACT → SUMMATION → DONE
4 | 25 | 2026-06-12 | Friday | Phase 1: FPGA Architecture Design | Constraint Unit Design | 4 | FALSE |  | Design constraint filtering as tensor masking.
4 | 26 | 2026-06-13 | Saturday | Phase 1: FPGA Architecture Design | Interface Design | 3 | FALSE |  | Design interface to O-DU emulator. Define data protocol.
4 | 27 | 2026-06-14 | Sunday | Phase 1: FPGA Architecture Design | Write Module Specs | 3 | FALSE |  | Create /docs/modules.md with Verilog module specifications.
4 | 28 | 2026-06-15 | Monday | Phase 1: FPGA Architecture Design | Week 4 Review | 3 | FALSE |  | Review designs. Identify risks. Update timeline.
5 | 29 | 2026-06-16 | Tuesday | Phase 2: FPGA Implementation | Verilog: BRAM Wrapper | 4 | FALSE |  | Write Verilog module for BRAM with read/write control.
5 | 30 | 2026-06-17 | Wednesday | Phase 2: FPGA Implementation | Verilog: Fixed-Point Arithmetic | 4 | FALSE |  | Implement fixed-point multiplier using DSP48E.
5 | 31 | 2026-06-18 | Thursday | Phase 2: FPGA Implementation | Testbench: BRAM + Arithmetic | 4 | FALSE |  | Write testbenches. Simulate in Vivado.
5 | 32 | 2026-06-19 | Friday | Phase 2: FPGA Implementation | Verilog: 2x2 Matrix Multiplier | 4 | FALSE |  | Implement core 2x2 matrix multiplier (quad-tile building block).
5 | 33 | 2026-06-20 | Saturday | Phase 2: FPGA Implementation | Testbench: 2x2 Multiplier | 4 | FALSE |  | Test with random matrices. Compare against Python.
5 | 34 | 2026-06-21 | Sunday | Phase 2: FPGA Implementation | Verilog: Block Controller | 3 | FALSE |  | Implement controller managing multiple 2x2 blocks in parallel.
5 | 35 | 2026-06-22 | Monday | Phase 2: FPGA Implementation | Buffer/Integration | 3 | FALSE |  | Integrate modules. Run basic simulation.
6 | 36 | 2026-06-23 | Tuesday | Phase 2: FPGA Implementation | Verilog: Tensor Contraction (Level 1) | 4 | FALSE |  | Implement first contraction step (multiplication within K blocks).
6 | 37 | 2026-06-24 | Wednesday | Phase 2: FPGA Implementation | Verilog: Tensor Contraction (Level 2) | 4 | FALSE |  | Implement summation over K blocks (linear scaling).
6 | 38 | 2026-06-25 | Thursday | Phase 2: FPGA Implementation | Testbench: Contraction | 4 | FALSE |  | Test contraction for D_b=2,4. Verify against Python.
6 | 39 | 2026-06-26 | Friday | Phase 2: FPGA Implementation | Verilog: Pipelined Version | 4 | FALSE |  | Add pipeline registers to improve throughput.
6 | 40 | 2026-06-27 | Saturday | Phase 2: FPGA Implementation | Performance Simulation | 4 | FALSE |  | Measure clock cycles. Compare pipelined vs unpipelined.
6 | 41 | 2026-06-28 | Sunday | Phase 2: FPGA Implementation | Optimization | 3 | FALSE |  | Identify bottlenecks. Optimize critical paths.
6 | 42 | 2026-06-29 | Monday | Phase 2: FPGA Implementation | Documentation | 2 | FALSE |  | Update /docs/implementation.md with contraction module details.
7 | 43 | 2026-06-30 | Tuesday | Phase 2: FPGA Implementation | Verilog: Jacobi Rotation Core | 4 | FALSE |  | Implement 2x2 Jacobi rotation (CORDIC or LUT).
7 | 44 | 2026-07-01 | Wednesday | Phase 2: FPGA Implementation | Verilog: Diagonal Block Processing | 4 | FALSE |  | Implement parallel diagonal block processing.
7 | 45 | 2026-07-02 | Thursday | Phase 2: FPGA Implementation | Verilog: Off-Diagonal Update | 4 | FALSE |  | Implement propagation to off-diagonal blocks.
7 | 46 | 2026-07-03 | Friday | Phase 2: FPGA Implementation | Testbench: SVD Step | 4 | FALSE |  | Test one Jacobi sweep. Compare vs numpy.linalg.svd.
7 | 47 | 2026-07-04 | Saturday | Phase 2: FPGA Implementation | Verilog: Convergence Control | 3 | FALSE |  | Implement logic to repeat sweeps until convergence.
7 | 48 | 2026-07-05 | Sunday | Phase 2: FPGA Implementation | Integration: Contraction + SVD | 4 | FALSE |  | Connect contraction and SVD for iTEBD-style iteration.
7 | 49 | 2026-07-06 | Monday | Phase 2: FPGA Implementation | Integration Test | 4 | FALSE |  | Run end-to-end simulation for small D_b=2.
8 | 50 | 2026-07-07 | Tuesday | Phase 2: FPGA Implementation | Verilog: Grover Diffusion Operator | 4 | FALSE |  | Implement diffusion as tensor contraction.
8 | 51 | 2026-07-08 | Wednesday | Phase 2: FPGA Implementation | Verilog: Amplitude Amplification Loop | 4 | FALSE |  | Implement sqrt(N) iterations of Grover.
8 | 52 | 2026-07-09 | Thursday | Phase 2: FPGA Implementation | Testbench: Grover for Small N | 4 | FALSE |  | Test Grover for N=4,8,16. Verify correct item found.
8 | 53 | 2026-07-10 | Friday | Phase 2: FPGA Implementation | Verilog: Constraint Unit | 4 | FALSE |  | Implement constraint filtering as tensor masking.
8 | 54 | 2026-07-11 | Saturday | Phase 2: FPGA Implementation | Verilog: Utility Calculation | 4 | FALSE |  | Implement sum-rate computation for each allocation.
8 | 55 | 2026-07-12 | Sunday | Phase 2: FPGA Implementation | Integration: Full Q-xApp | 4 | FALSE |  | Connect State Prep → Grover Loop → Measurement
8 | 56 | 2026-07-13 | Monday | Phase 2: FPGA Implementation | Full System Test | 4 | FALSE |  | Test with 3 UEs, 4 PRBs (paper's test case).
9 | 57 | 2026-07-14 | Tuesday | Phase 3: Testing & Benchmarking | Reproduce Paper Test | 4 | FALSE |  | Run FPGA emulator for 3 UE, 4 PRB. Compare to Q-xApp paper.
9 | 58 | 2026-07-15 | Wednesday | Phase 3: Testing & Benchmarking | Accuracy Analysis | 4 | FALSE |  | Measure % error from optimal. Target <1%.
9 | 59 | 2026-07-16 | Thursday | Phase 3: Testing & Benchmarking | Latency Measurement | 4 | FALSE |  | Measure end-to-end latency in cycles. Convert to microseconds.
9 | 60 | 2026-07-17 | Friday | Phase 3: Testing & Benchmarking | Compare to Qiskit | 3 | FALSE |  | Run same problem in Qiskit. Compare latency.
9 | 61 | 2026-07-18 | Saturday | Phase 3: Testing & Benchmarking | Scaling Test 1 | 4 | FALSE |  | Increase to 4 UE, 6 PRB. Measure scaling.
9 | 62 | 2026-07-19 | Sunday | Phase 3: Testing & Benchmarking | Scaling Test 2 | 4 | FALSE |  | Increase to 5 UE, 8 PRB. Measure scaling.
9 | 63 | 2026-07-20 | Monday | Phase 3: Testing & Benchmarking | Document Results | 3 | FALSE |  | Create /results/scaling_results.md with tables and graphs.
10 | 64 | 2026-07-21 | Tuesday | Phase 3: Testing & Benchmarking | CPU Baseline (Exhaustive) | 4 | FALSE |  | Implement exhaustive search in Python. Measure time.
10 | 65 | 2026-07-22 | Wednesday | Phase 3: Testing & Benchmarking | CPU Baseline (Greedy) | 4 | FALSE |  | Implement greedy algorithm from paper.
10 | 66 | 2026-07-23 | Thursday | Phase 3: Testing & Benchmarking | CPU Baseline (Genetic) | 4 | FALSE |  | Implement GARAA from paper.
10 | 67 | 2026-07-24 | Friday | Phase 3: Testing & Benchmarking | GPU Comparison | 4 | FALSE |  | Run comparison on GPU using PyTorch/TensorFlow.
10 | 68 | 2026-07-25 | Saturday | Phase 3: Testing & Benchmarking | Create Benchmark Table | 4 | FALSE |  | Compile: Algorithm ¦ Time ¦ Accuracy ¦ Hardware
10 | 69 | 2026-07-26 | Sunday | Phase 3: Testing & Benchmarking | Plot Results | 3 | FALSE |  | Create log-log scaling, accuracy, speedup plots.
10 | 70 | 2026-07-27 | Monday | Phase 3: Testing & Benchmarking | Document Benchmark | 3 | FALSE |  | Write /results/benchmarking.md with complete analysis.
11 | 71 | 2026-07-28 | Tuesday | Phase 4: Documentation & Final Report | Chapter 1: Introduction | 4 | FALSE |  | Background, problem statement, motivation, research questions.
11 | 72 | 2026-07-29 | Wednesday | Phase 4: Documentation & Final Report | Chapter 2: Literature Review | 5 | FALSE |  | O-RAN, quantum search, tensor networks, FPGA acceleration.
11 | 73 | 2026-07-30 | Thursday | Phase 4: Documentation & Final Report | Chapter 3: Methodology | 5 | FALSE |  | Tensor network Grover, quad-tile partitioning, FPGA architecture.
11 | 74 | 2026-07-31 | Friday | Phase 4: Documentation & Final Report | Chapter 4: Implementation | 5 | FALSE |  | Verilog modules, BRAM/DSP, control FSM, constraint unit.
11 | 75 | 2026-08-01 | Saturday | Phase 4: Documentation & Final Report | Chapter 5: Results (Part 1) | 4 | FALSE |  | Verification, scaling, comparison to Q-xApp paper.
11 | 76 | 2026-08-02 | Sunday | Phase 4: Documentation & Final Report | Chapter 5: Results (Part 2) | 4 | FALSE |  | Benchmarking, accuracy, real-time feasibility.
11 | 77 | 2026-08-03 | Monday | Phase 4: Documentation & Final Report | Chapter 6: Discussion | 3 | FALSE |  | Interpretation, limitations, comparison to prior work.
12 | 78 | 2026-08-04 | Tuesday | Phase 4: Documentation & Final Report | Chapter 7: Conclusion | 3 | FALSE |  | Summary, contributions, limitations, future work.
12 | 79 | 2026-08-05 | Wednesday | Phase 4: Documentation & Final Report | Abstract & References | 3 | FALSE |  | Write abstract, format IEEE references, acknowledgments.
12 | 80 | 2026-08-06 | Thursday | Phase 4: Documentation & Final Report | Figures & Tables | 4 | FALSE |  | Create/format all figures and resource utilization tables.
12 | 81 | 2026-08-07 | Friday | Phase 4: Documentation & Final Report | First Full Draft | 4 | FALSE |  | Compile all chapters. Check flow and consistency.
12 | 82 | 2026-08-08 | Saturday | Phase 4: Documentation & Final Report | Self-Review & Editing | 4 | FALSE |  | Fix grammar, clarity, formatting.
12 | 83 | 2026-08-09 | Sunday | Phase 4: Documentation & Final Report | Supervisor Review | 3 | FALSE |  | Send to supervisor. Incorporate feedback.
12 | 84 | 2026-08-10 | Monday | Phase 4: Documentation & Final Report | Final Polish | 4 | FALSE |  | Final edits. Generate PDF. Prepare appendices.

## Weekly Summary
Week | Total Hours | Total Tasks | Cumulative Hours | Phase
1 | 20 | 7 | 20 | Phase 0: Setup & Initial Pitch
2 | 20 | 7 | 40 | Phase 0: Setup & Initial Pitch
3 | 24 | 7 | 64 | Phase 1: FPGA Architecture Design
4 | 24 | 7 | 88 | Phase 1: FPGA Architecture Design
5 | 26 | 7 | 114 | Phase 2: FPGA Implementation
6 | 25 | 7 | 139 | Phase 2: FPGA Implementation
7 | 27 | 7 | 166 | Phase 2: FPGA Implementation
8 | 28 | 7 | 194 | Phase 2: FPGA Implementation
9 | 26 | 7 | 220 | Phase 3: Testing & Benchmarking
10 | 26 | 7 | 246 | Phase 3: Testing & Benchmarking
11 | 30 | 7 | 276 | Phase 4: Documentation & Final Report
12 | 25 | 7 | 301 | Phase 4: Documentation & Final Report
TOTAL

## Milestones
Milestone | Day | Deliverable | Description
Week 2 | 9 | Initial Project Pitch | 10 slides presented
Week 3 | 21 | Architecture Document | Block diagrams complete
Week 6 | 42 | Tensor Contraction Module | Working in simulation
Week 8 | 56 | Complete Q-xApp Emulator | Full system working
Week 10 | 70 | Benchmarking Complete | Results vs CPU/GPU
Week 11 | 77 | First Draft Report | 30-40 pages
Week 12 | 84 | Final Report | 20-50 pages + code + presentation